## Gantchart
GANTT CHART
PROJECT TITLE |  | Simple Social Media Platform to connect with college peers |  |  |  |  | YEAR | [6 empty] | SE
PROJECT GUIDE |  | Dr. Pravin Adivarekar |  |  |  |  | DATE | [6 empty] | 15/5/2021
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Problem search | Devansh, Riddhi, Aditya, Shauryan | 2020-05-10 | 2020-07-11 | 3 | 100% | bar: WEEK 1 M to WEEK 2 F; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.1.1 | Problem finalization | Devansh, Riddhi, Aditya, Shauryan | 2020-07-11 | 2020-07-11 | 1 | 100% | bar: WEEK 2 M to WEEK 3 M; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.2 | Project Title | Riddhi | 20/11/2020 | 23/11/2020 | 1 | 100% | bar: WEEK 3 T to WEEK 3 W; WEEK 3 F; WEEK 4 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.3 | Abstract | Riddhi | 20/11/2020 | 23/11/2020 | 2 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 4 W; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.4 | Problem Definition | Devansh, Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100% | bar: WEEK 4 F to WEEK 5 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.5 | Objectives | Devansh, Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100% | bar: WEEK 5 M; WEEK 6 M; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.6 | Scope | Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100% | bar: WEEK 5 M to WEEK 5 W; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.7 | Existing System/Project | Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100% | bar: WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.8 | Technology stack | Devansh, Aditya, Shauryan | 2020-10-12 | 15/12/2020 | 1 | 100% | bar: WEEK 6 M to WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.9 | Benefits for environment | Riddhi | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.1 | Benefits for society | Riddhi | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
1.11 | Applications | Devansh, Riddhi | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2 | Project Design
2.1 | Proposed System | Shauryan, Aditya | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 M to WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.2 | Design(Flow Of Modules) | Devansh, Aditya, Shauryan | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 M to WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.3 | Data Flow Diagram | Devansh, Aditya, Shauryan | 2020-10-11 | 15/12/2020 | 1 | 100% | bar: WEEK 6 M to WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.4 | Modules
2.4.1 | Module-1: Landing, Login, and Register | Riddhi, Shauryan, Devansh, Aditya | 17/2/2021 | 2021-05-03 | 3 | 100% | bar: WEEK 7 T to WEEK 7 R; WEEK 8 M to WEEK 8 W; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.4.2 | Module-2: User profile | Riddhi, Shauryan, Devansh, Aditya | 2021-12-03 | 15/4/21 | 5 | 100% | bar: WEEK 6 T to WEEK 6 W; WEEK 6 F; WEEK 7 R to WEEK 7 F; WEEK 8 W to WEEK 9 T; WEEK 9 R to WEEK 9 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.4.3 | Module-3: Dashboard | Riddhi, Shauryan, Devansh, Aditya | 20/4/2021 | 2021-10-05 | 4 | 100% | bar: WEEK 6 R; WEEK 8 F to WEEK 9 T
2.4.4 | Module-4: Navbar | Riddhi, Shauryan, Devansh, Aditya | 17/4/2021 | 2021-10-05 | 4 | 100% | bar: WEEK 8 R to WEEK 8 F; WEEK 9 W to WEEK 9 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.4.5 | Module-5: Posts | Devansh | 20/3/2021 | 11/5.2021 | 3 | 25% | bar: WEEK 8 R to WEEK 8 F; WEEK 9 R; WEEK 11 M; WEEK 11 R to WEEK 11 F
2.4.5 | Preparation Of Report | Riddhi, Aditya, Shauryan, Devansh | 2020-10-12 | 15/12/2020 | 2 | 100% | bar: WEEK 5 F to WEEK 6 T; WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F
3 | Project Implementation
3.1 | Module-1: Routes | Riddhi, Shauryan, Devansh, Aditya | 17/2/2021 | 2021-05-03 | 2 | 100% | bar: WEEK 8 F; WEEK 10 M to WEEK 10 T; WEEK 10 R to WEEK 11 M; WEEK 11 R to WEEK 11 F
3.2 | Module-2: Middleware | Riddhi, Shauryan, Devansh, Aditya | 20/4/2021 | 2021-10-05 | 2 | 100% | bar: WEEK 8 F; WEEK 10 F to WEEK 11 T; WEEK 11 R to WEEK 12 M
3.3 | Module-3: Models | Riddhi, Shauryan, Devansh, Aditya | 17/4/2021 | 2021-10-05 | 3 | 100% | bar: WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 12 T
3.4 | Module-4 | Riddhi, Shauryan, Devansh, Aditya | 17/4/2021 | 2021-10-05 | 3 | 75% | bar: WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F; WEEK 12 T to WEEK 12 R
4 | Results and Analysis
4.1 | Analysis Of Results | Riddhi | 2021-04-05 | 2021-04-05 | 1 | 100% | bar: WEEK 8 F; WEEK 11 M; WEEK 11 R to WEEK 11 F; WEEK 12 W
4.2 | Report Preparation | Riddhi | 2021-03-05 | 2021-10-05 | 1 | 100% | bar: WEEK 12 T to WEEK 12 F